## Migration Process
Process | Process Owner | Run Frequency | New Location | Changes to Script Completed | Moving of History Data Required | Moving of Data Completed | Process Completed | Person Responsible | Comments
BNM_Daily_Run | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Processes Being Turned Off
Call_Centre_Daily_Monitoring | Bevan | Daily | Prd_ContactInfo | Yes | Yes | No | No | Phumudzo
CIC_Call_Mapping | Bevan | Daily | Prd_ContactInfo | Yes | TBC | TBC | No | Phumudzo
Prob2activate_Monthly_Scores | Kyle | Monthly | Prd_Collections_Strategy | Yes | Yes | No | No | Dustin/Siphe
Prob2Honour_Extract_Score | Kyle | Monthly | Prd_Collections_Strategy | No | Yes | No | No | Kyle
Call_Centre_Strategy_Upload | Bevan/Kyle | Daily | Prd_ContactInfo | ??? | Yes | No | No | Phumudzo
CIC_Call_Mapping_Report | Bevan | Daily | TBC | No | TBC | No | No | Phumudzo
BNM_Daily_Run_V2 | Kyle | Daily | Prd_ContactInfo | Yes | Yes | No | No | Kyle
BCP_Score | Bevan | Daily | Prd_ContactInfo | Yes | Yes | No | No | Phumudzo
PTP_Daily_Tables_Update | Bevan | Daily | TBC | No | TBC | No | No | Phumudzo
BHT_Dialler_BCP_Numbers | Bevan | Daily | Prd_Collections_Strategy | Yes | Yes | No | No | Phumudzo
Work_Number_Delete | Kyle | Daily | N/A | N/A | N/A | N/A | N/A | N/A | Writes to a SAS Dataset
BNM_Monitoring | Kyle | Daily | Prd_ContactInfo | Yes | Yes | No | No | Kyle
Share_BNM_Daily_Stats | Kyle | Daily | Prd_ContactInfo | Yes | No | N/A | Yes | Kyle
BNM_Daily_Monitoring | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Legacy Process - No ownership
BNM_Daily_Check | Kyle | Daily | Prd_ContactInfo | Yes | Yes | No | No | Kyle
Monthly_Coldata | Dustin??? | Monthly | Prd_Collections_Strategy | Yes | Yes | No | No | Dustin/Siphe
Prob2Actv Monitoring | Kyle | Daily | Prd_Collections_Strategy | Yes | Yes | No | No | Kyle
KJM_EDC_Ranking | Kyle | Daily | Prd_Collections_Strategy | Yes | Yes | No | No | Kyle
Collections_Target | Kyle | Daily | Prd_Collections_Strategy | Yes | Yes | No | No | Kyle